## Management
ANNUAL PLAN OF ACTION AND MANAGEMENT FOR THE STRENGTHENING OF HUMAN RIGHTS MANAGEMENT AT TGI Due Diligence - Gap Closing and Risk Management in Human Rights
GENERAL OBJECTIVE: To contribute to the positioning, genuine liasing, and the protection of TGI's reputation through the implementation of good practices in the management of Human Rights in accordance with international standards in this matter, and the traceability of such best practices before TGI's internal and external stakeholders. This, with a double perspective aligned with the Sustainable Development objectives and strategy: (i) Consolidation of due diligence in human rights for the prevention an control of risks to human rights associated with the Company's activities and its value chain. (ii) Adding value by contributing to the conditions for the fulfillment of human rights in the operation's environment.
STRATEGIC LINE | OBJECTIVE | HHRR RISK(S) | ACTIVITY | DESCRIPTION | MAIN AREA(S) INVOLVED | SUPPORT AREA(S) INVOLVED | TIME PERIOD PROPOSED
I. STRENGTHENING OF HUMAN RIGHTS MANAGEMENT (In line with the Guiding Principles on Business and Human Rights- UNGPs)
Implementation of the political commitment with regard to human rights and the coordination of corporate policies. | To have a Human Rights corporate policy which establishes the principles and criteria for internal action, and gives an account of the company's commitment to the respect of human rights before internal and external stakeholders. | N.A. | Creation and implementation of TGI's Human Rights Policy* * This action is included in the plan because it responds to one of the opportunities for improvement identified, but it is subject matter of the consultancy with Trust and will be carried out during the first trimester of 2021. | To formulate and implement TGI's Human Rights Policy GENERAL ACTIVITIES: a. To identify relevant human rights and populations according to the nature of the company and the characteristics of its activities, as well as the operation's environment. b. Creation of a sector-specific benchmarking. c. To carry out internal consultations through interviews. d. To define a strategic focus, commitments, governance structure, and criteria for action, as well as the mechanisms for implementation. c. To establish compliance expectations and commitments regarding business allies (contractors and suppliers, clients, institutional allies). d. To draft the Human Rights Policy proposal. e. To validate internally. f. To carry out the process of implementation in accordance with internal guidelines. | - Sustainable Development Management | - Board of Directors - Chair's Office | First semester 2021
Communication and internal training | To create awareness of and to strengthen the knowledge collaborators have regarding human rights management in the corporate field in order to influence organizational culture with a focus on human rights . | N.A. | Design and implementation of an internal communications plan regarding TGI's Human Rights Policy | To define and enforce an internal communications strategy for the Human Rights Policy with the purpose of making its contents known and generating an understanding about the strategic importance of human rights in a responsible corporate management for TGI, the scope of the commitments and the implications for management. GENERAL ACTIVITIES: a. To formulate specific objectives for the communications plan, which shall be directed toward ethical reflection, strategic importance, and the usefulness of the guidelines on human rights based on the organization's strategic objectives, as well as those specific to different areas. b. To identify categories of target audiences in order to adapt language, general contents, and communication channels. c. To define key messages and pertinent communication pieces for different audiences, which highlight conceptual elements, commitments, their relation to other corporate guidelines, and management in different areas. This, while ensuring relevance and considering the corporate field and seeking the recepient's participation or interaction. d. To create and disseminate a Questions/Answers document about the Human Rights Policy. | - Sustainable Development Management | - Office of the Assistant Director for Communications | Second semester 2021
|  |  | Design and implementation of an external communications plan regarding TGI's Human Rights Policy | To define and enforce an internal communications strategy for the Human Rights Policy with the purpose of making its contents known to external stakeholders. GENERAL ACTIVITIES: a. To identify categories of target audiences in order to adapt language, general contents, and communication channels. b. To post the policy on channels that are accessible to all stakeholders in the company. c. To define key messages and pertinent communication pieces for different audiences, which highlight conceptual elements, commitments, their relation to other corporate guidelines, and management in different areas. This, while ensuring relevance and considering the corporate field and seeking the recepient's participation or interaction. d. To establish criteria in order to determine the level of effectiveness of the strategy and messages. | - Sustainable Development Management - Office of the Legal and Services Vice-chair. | - Office of the Assistant Director of Communications | Second semester 2021
|  |  | Creation and implementation of an internal training plan on human rights. | To formulate an annual for colaborators and to determine implementation cycles. GENERAL ACTIVITIES: a. Creation of content for the basic virtual course on human rights (*it will be created in the framework of the consultancy developed by Trust) b. Technological design and structure for the basic virtual course on human rights. c. To establish training goals, a public objective, and a annual enforcement plan. c. To establish criteria regarding frequency, and updates to the personnel. d. To created specialized courses on HHRR directed to specific areas of TGI. These courses shall be directed to collaborators with duties in the following areas: environmenal, human resources management, physical safety, administrative services (Queries, Complaints, Claims), and social management. e. To integrate the human rights subject into the training cycles on ethics and compliance. | - Sustainable Development Management - Human Resources Management | - Office of the Assistant Director for Communications | Second semester 2021
Management of Due Diligence in Human Rights | To ensure human rights management in a systemic, coordinated and traceable way, toward continuous improvement of the company's performance in this matter. | N.A. | Design and implementation of a due diligence model in human rights | To define and implement a human rights management model, which integrantes the different areas of the Company in a systemic, coordinated and coherent way. GENERAL ACTIVITIES: a. Definition of objectives, general scope based on the Human Rights Policy. b. Definition of components, governance structure, roles and responsibilities at the Company's various levels. c. Processes design and definition of indicators d. Model documentation. e. Formulation of an implementation plan. | - Planning and Performance Management - Sustainable Development Management |  | Second semester 2021
|  |  | Design and implementation of a methodology of risk analysis in human rights | Creation of methodological guidelines for risk analysis in human rights coordinated with TGI's risk management model. GENERAL ACTIVITIES: a. Definition of focus for the coordination of risk management in human rights with the general risk model through management in all of the company's areas. b. Definition of methodology for risk identification, assessment, and management in human rights. c. Dissemination and training. d. Formulation of an implementation plan. | - Planning and Performance Management - Sustainable Development Management |  | First semester 2022
|  |  | To carry out a risk and impact analysis on human rights related to specific projects or operations | To carry out a risk and impact analysis on human rights related to specific projects or operations GENERAL ACTIVITIES : a. Definition of the scope based on the identification and prioritization of projects/operation or territorial settings. b. Definition of an enforcement plan. c. To carry out a risk analysis on human rights related to specific projects and operations in order to manage specific risks and their corresponding plans of action. | - Sustainable Development Management |  | Second semester 2021
Securing human rights management in value chain | To strengthen internal skills and mechanisms to ensure the alignment of business associates with the Human Rights Policy, as well as ensuring risk prevention. | N.A. | Inclusion of due diligence in human rights to the process of contractors' management | To establish the guidelines and mechanisms of securing due dilengence in human rights to the process of contractors' management, so that they are integrated to the HSEQ and Social Manuals for Contractors and Suppliers. GENERAL ACTIVITIES: a. To review and complete the registration questionaire for suppliers in order to incorporate specific questions related to human rights management whose completion is mandatory (human rights policy, due diligence process, risk analysis, internal training, among others). b. To define specific contractual requirements (clase or annex) related to human rights management, in accordance with contractors' categorization. c. To include human rights indicators for the monitoring and evaluation of contractors' and suppliers' performance. d. To train contract supervisors. e. To include matters relating to HHRR in oversight plans for contractors and in check lists in accordance with contractual requirements and defined indicators. | - Supply Management - Office of the Legal and Services Vice-chair. | - Sustainable Development Management | First semester 2022
|  |  | Creation of content for induction training in human rights for contractors and suppliers | Creation of a basic virtual course on human rights for contractors' induction training GENERAL ACTIVITIES: a. Creation of contents for the basic virtual course on human rights (*it will be created in the framework of the consultancy developed by Trust) b. Technological design and structure for the basic virtual course on human rights. c. To establish training goals, a public objective, and a annual enforcement plan. c. To establish criteria regarding frequency, and updates to the personnel. | - Supply Management | - Sustainable Development Management | Second semester 2021
|  |  | Implementation of a cooperation and incentives system for due diligence for contractors and suppliers | To enforce cooperative strategies from the contractors' perspective as TGI's allies, geared toward aligning interests shared knowledge and incentives that lead to the implementation of due diligence processes in human rights in their own supply chains. GENERAL ACTIVITIES: a. To design and to set in motion a dialogue and joint analysis mechanism (Collaborative Assessment) with suppliers and contractors for the issuance of a base line of human rights management that goes beyond the first link in the chain. b. To carry out an alliance with strategic suppliers and contractors for the construction of knowledge and the identification of opportunities of cooperative and coordinated work to strengthen human rights management in the supply chain. c. To design and set in motion joint strategies for human rights management with suppliers and contractors in territories where they are located. d. To establish incentives (acknowledgement) granted to contractors and suppliers who are outstanding in their human rights management. e. To create a case study jointly to show the progress made with regard to best practices related to human rights management in the chain of supply. It can be submitted to institutions such as UN Global Compact Sustainable Supply Chains. | - Supply Management | - Sustainable Development Management | First semester 2022
Strengthening of claim submission mechanisms | To align internal claim submission mechanisms with principles of effectiveness established by the United Nations' Guiding Principles | R7 | Review and adjustment of claim submission mechanisms. | To carry out an in-depht review and adjustment of the Queries, Complaints, Claims mechanism (PQRS Procedure) to ensure that all effectiveness criteria in human rights are in accordance with the standards of best practices. GENERAL ACTIVITIES: a. To do an in-depth review of the PQRS procedure b. To identify user perceptions about the application of the mechanism's effectiveness criteria. c. To define adjustements to the procedure (rights classification system according to severity, petitioner's catergory, cultural adaptation in specific territories, definition of scaling up, and resolution criteria). d. Inclusion of a sub-procedure for continuous improvement coordinated with the PQRS procedure. e. Implementation and training plan. | - Office of the Director of Administrative Services - Sustainable Development Management - Office of the Legal and Services Vice-chair. | - Office of the Assistant Director of Social Management | Second semester 2021
|  |  | Structuring a model for knowledge management for the continuous improvement within the framework of the claim submission mechanism. | To create and implement a procedure directed at the continuous improvement of performance in the Company's areas in the application of the PQRS procedure, as well as the application of their own procedures based on the inputs generated by the mechanism. GENERAL ACTIVITIES: a. To design a periodic and systemic application outline containing: - Identification of repeating matters resulting in a querie, complaint or claim based on quantitative indicators from the PQRS system. - Selection of matters to be analyzed - Definition of spaces, participants, and methodologies for the identifications of shortcomings or detours in the assistance with and solution of queries, complaints or claims or that may constitute the causes of said queries, complaints or claims submitted to the Company. This is to be done through a cause-root analysis, as well as the identification of learned lessons and improvement measures . - Dissemination and implementation of improvement measures with regard to Company guidelines, procedures or practices | - Sustainable Development Management - Office of the Director of Administrative Services |  | First semester 2022
II. LINES OF ACTION FOR STRENGTHENING HUMAN RIGHTS MANAGEMENT IN SPECIFIC MATTERS
Intercultural liasing | To have internal skills for due diligence management in the framework of intercultural liasing | R3 | Definition and implementation of operative guidelines regarding inter-cultural liasing. | To implement a protocol of due diligence with regard to prior consent and inter-cultural liasing with ethnic communities, coordinated with the Social Management Plan, (Subcomponent of Intercultural Liasing, which establishes guidelines in the framework of projects and operations regarding: (i) identification of ethnic communities; (ii) determination of direct impacts; (iii) action principles and criteria for eventual prior consent procedures; (iv) principles and criteria for liasing in technical and social investment participation. | -Office of the Assistant Director of Social Management | - Project Management | Second semester 2021
|  |  | Training in inter-cultural liasing | Carrying out a training workshop regarding the rights of ethnic communities directed toward collaborators with direct duties in the matter (*the consultancy that is under way is in charge of this workshop). | - Sustainable Development Management |  | First semester 2022
Strengthening of due diligence management for the prevention of labor impacts in the framework of the pandemic | To ensure due diligence in risk management regarding impacts to workers derived from Covid 19. | R9 | Inclusion of due diligence measures in the strategy and plans of acction for the handling of Covid-19 | GENERAL ACTIVITIES: a. Identification of family, social, economic and cultural vulnerabilities, and analysis of psico-social risks derived from the measures established for the handling of the pandemic, in particular, regarding remote work , with a differential approach based on gender and considering family surroundings, particularly for children and adolescents. b. Definition and dissemination of guidelines and recommendations on self-care for the preventions of health risks associated to remote work (this activity can be conducted partnering with the Labor Risks Administrator (ARL)). c. Definition of a protocol for the use and handling of instruments and virtual tools for work, which establishes action principles and rules to find balance between family and work life, the prevention of stalking or any other form of undue pressure or harrassment; data and privacy protection. | - Office of the Director of COVID - 19 - Office of the Assistant Director for Welfare, Climate and Culture |  | Second semester 2021
Strengthening of due diligence management with a differential approach based on gender | To strengthen internal skills for the implementation of the Diversity and Inclusion Policy | R9, R6 | Certification process for the management system on gender equality | To continue with the process of certification for the Seal on Labor Gender Equality (EQUIPARES). In this framework, the conduction of the following activities will be ensured: GENERAL ACTIVITIES: a. To identify the existence of access barriers, whether they'd be direct or indirect, for women to various positions and fields, including middle and senior management, as well as to the company's Board of Directors, and to implement a plan for eliminating barriers. b. To establish goals for women to be able to fill positions of middle and senior management in the medium and long term. c. To carry out a procedure for the education of women, framed within the Individual Development Plan, seeking for them to fill management positions in the future. | - Human Resources Management |  | Under way
|  |  | Training for the Community Committee regarding diversity and inclusion | To strengthen the community committee's skills regarding diversity and inclusion through training in the matter. | - Human Resources Management |  | First semester 2022
|  |  | Extension of the work approach for the Diversity and Inclusion Policy | To carry out an anlysis of challenges and opportunities for the extention of the work approach relating to diversity and inclusion to fields such as ethnic diversity or gender diversity to diverse communities (LGBTI), in accordance with the Diversity and Gender Policy. | - Human Resources Management | - Sustainable Development Management | First semester 2022
|  |  | Extension of the Diversity and Inclusion Policy to the supply chain | To include a differential approach in relation to gender in the framework of securing the supply chain through: a. Inclusion of the Diveristy and Inclusion Policy in the contractual requirements with contractors and suppliers, and inclusion of oversight and assesment mechanisms. b. Definition of a case handling mechanism. | - Sustainable Development Management - Supply Management - Office of the Legal and Services Vice-chair. |  | First semester 2022
|  |  | To implement a strategy directed to the prevention, detection and handling of violence and harrassment situations against women. | To implement a strategy directed to the prevention, detection and handling of violence and harrassment situations agaisnt women in the framework of relationships among employees, among them and contractors, and in relationaships with communities, in accordance to the IFG guidelines: Gender-Based Violence and Harassment Emerging Good Practice for the Private Sector. GENERAL ACTIVITIES: a. To carry out a study related to vulnerabilities, conflict situations, and potential impacts of gender-based violence or harrassment in the framework of the workers/community interaction (in-depth study based on inputs already produced by TGI). b. To create a protocol directed to the prevention and handling of gender-based violence or harrassment in the framework of the workers/community interaction (this protocolo should be created in coordation with human resources, who is in charge of the management of matters in the direct interaction with employees). c. To develop an internal education plan about gender in the framework of the workers/community interaction. | - Sustainable Development Management - Supply Management - Office of the Legal and Services Vice-chair. |  | Second semester 2021
Differential approach: Children and adolescents (NNA for its initials in Spanish) | To include a differential approach for children and adolescents. | R8 | To include a differential approach for children and adolescents in various policies and mechanisms of due diligence in human rights management . | To include a differential approach for children and adolescents in human rights management . * This is done in coordination with other actions and approaches in the plan of action | - Sustainable Development Management | - Human Resources Management - Office of the Assistant Director for Welfare, Climate and Culture - Supply Management | Second semester 2021
Security | To ensure the traceability and to institutionalize the knowledge of due diligence in human rights in the management of physical security. | R10 | Design and implementation of the process of due diligence in human rights with regard to physical security | To define a procedure, methodologies and instruments for the analysis and monitoring of human rights risks associated to safety matters, in accordance to the UNGP standards and the Voluntary Principles on Security and Human Rights. GENERAL ACTIVITIES: a. To define and document the guidelines, methodology, and forms to carry out the analysis and monitoring of human rights risks in coordination with risk analysis in security. b. To establish and enforce the implementation plan in cooperation with the security contractor. | - Office of the Director of Administrative Services - Physical Security - Sustainable Development Management |  | Second semester 2021
|  |  | Training in security and human rights | To develop training activities in security and human rights directed to security collaborators and contractors who work directly with the company, with an emphasis on due diligence regarding human rights. | - Office of the Director of Administrative Services - Physical Security - Sustainable Development Management |  | First semester 2021
|  |  | Definition of a human right contractual clause on physicial security contracts | GENERAL ACTIVITIES: a. To carry out a diagnosis on the management of human rights with the contractor for physicial security (collaborative assessment) and to identify improvement opportunities. b. To define specific contractual requirements on human rights for security contracts and indicators for its oversight, and to implement requirements in accordance to the terms of validity in the contract. | - Office of the Director of Administrative Services - Physical Security - Supply management | - Sustainable Development Management | First semester 2021
|  |  | Liasing with armed forces regarding human rights and security | To hold a meeting with the Office for Human Rights at the National Ministry of Defense to inform about TGI's Human Rights Policy, to establish work opportunities in the framework of the HHRR component in security agreements to strengthen best prácticas, in accordance with implementation action for the Voluntary Principles by the Ministry of Defense. | - Office of the Director of Administrative Services - Physical Security - Sustainable Development Management |  | Second semester 2021
|  |  | Documentation of the protocol for crisis handling for the inclusion of the human rights perspective | To document guidelines, action criteria and procedures for the handling of crisis situations that merit the intervention of the security area and the armed forces in coordination with Social Management. | - Office of the Director of Administrative Services - Physical Security | - Sustainable Development Management - Office of the Director of Social Management. | Second semester 2021
Rural property management | To clear all situations where there is a lack of recognition to rights holders of their property rights in lands where easements are not established. | R4 | Continuity to the plan of property clearing. | To give continuity to the plan for identification and definition of the properties' legal situation and to the plan of property clearing. | - Land Directorate |  | First semester 2021
| To prevent situations which could lead to impacts to the rights of victims of dispossession or forced abandonment of their properties. | R5 | Securing due diligence regarding land restitution | Review of the application and effectiveness of institutional consultation measures established by the Manual on Land Management for the verification of land restitution procedures in areas surrounding projects and operations. GENERAL ACTIVITIES: a. To verify frequent consultation on the information about procedures of demarcation of the lands and restitution requests, and to strengthen frequent liasing with the Land Restitution Unit (URT for its initials in Spanish) in surrounding areas relevant to project execution in order to get to know the URT's priorities in an opportune manner, as well as the development of procedures from the administrative phase, to an eventual initiation of a judicial proceeding. c. To ensure the detailed documentation of the due diligence procedure carried out with respect to lands subject to restitution requests. d. To ensure the supply of internal information about lands subjec to restitution requestos or that have already been restituted in order to establish liasing strategies, and access to lands in the framework of project or operation execution that allows for the reduction or risks derived from an inappropriate liasing and communication with occupiers or victims. | - Land Directorate - Office of the Assistant Director of Social Management. | - Office of the Vice-chair of construction - Office of the Vice-chair of operations | First semester 2021
Environment | To strengthen actions for the mitigation of impacts associated to noise, smells and lights | R2 | Strengthening of preventive actions and mitigation with respect to noise, smell emission and light | a. To ensure the adequacy of technical and social criteria for the determiantion of impacts associated to noise, smells and lights in the maturing cycle of projects in order to ensure its prevention and the establishment of adequate mitigation measures b. To ensure the continuity of the Noise Mitigation Plan based on prioritization of situations with a highr impact in order to ensure compliance to appliable regulation and the implementation of mitigation actions. In this framework, | - Sustainable Development Management - Office of the Assistant to the Director of Environment |  | First semester 2021
|  |  | Strengthening of communication with interested parties in relation to noise | To define a communications and liasing plan at prioritized surrounding areas in order to improve the perception communities have about net benfits related to TGI's projects and operations. GENERAL ACTIVITIES: a. To carry out work with the communities oriented to their understanding of the tangible benefits versus the discomfort caused by the presence of operations. b. To establish mechanisms of communication with the communities about monitoring actions, compliance with the maximum levels allowed, and mitigation measures implemented, as well as about the knowledge of problems associated with other sources of impact to the levels of environmental noise. | - Sustainable Development Management - Office of the Assistant to the Director of Environment |  | First semester 2021
Resettlement | To ensure due diligence regarding human rights for involuntary resettlement procedures | R8, R6 | Due diligence analysis regarding human rights in resettlement procedures under way. | To develop a due diligence analysis on human rights in resettlement procedures under way in order to strengthen measures for their guarantee and the prevention of impacts derived from its planning or enforcement. | - Sustainable Development Management - Office of the Assistant to the Director of Environment |  | Second semester 2021
|  |  | Review and adjustments to the Resettlement Manual | To identify lessons learned and good practices in resettlement prcedures in order to establish improvements in the Resettlement Manual and to include action principles and criteria to respond to international and constitutional guidelines about human rights, and to adjust the procedure and analysis instruments to ensure it. Particularly, regarding inclusion of differential criteria (gender-based, children and adolescents, senior citizens) to determine socio-economic vulnerabilities, the strenthening of the identification and analysis of tangible cultural impact, attention to impacts associated to ressettlement in communities or social units not associated to the resettlement. | - Sustainable Development Management - Office of the Assistant to the Director of Environment |  | Second semester 2021
JUDICIAL RULINGS WITH A POTENTIAL TO IMPACT HHRR | To ensure due diligence regarding human rights in compliance with rulings with the potential to generate impacts to said rights and to prevent new judicial proceedings. | R4 | Due diligence analysis in the compliance with rulings. | To establish guidelines and mechanisms to ensure complicance with Rulings or determinations by administrative authorities related to HHRR To monitor compliance with judicial and/or administrative orders related to HHRR of which the company is in charge. To strengthen direct claim submission mechanisms and/or PQRS, among others, as preventive tools in relation to the infringement of HHRR. | - Sustainable Development Management - Office of the Assistant to the Director of Environment - Office of the Director of Judicial Proceedings |  | Second semester 2021

## Added Value
ANNUAL PLAN OF ACTION AND MANAGEMENT FOR THE STRENGTHENING OF HUMAN RIGHTS MANAGEMENT AT TGI Due Diligence - Gap Closing and Risk Management in Human Rights
GENERAL OBJECTIVE: To contribute to the positioning, genuine liasing, and the protection of TGI's reputation through the implementation of good practices in the management of Human Rights in accordance with international standards in this matter, and the traceability of such best practices before TGI's internal and external stakeholders. This, with a double perspective aligned with the Sustainable Development objectives and strategy: (i) Consolidation of due diligence in human rights for the prevention an control of risks to human rights associated with the Company's activities and its value chain. (ii) Adding value by contributing to the conditions for the fulfillment of human rights in the operation's environment.
STRATEGIC LINE | OBJECTIVE | ACTIVITY | DESCRIPTION | MAIN AREA(S) INVOLVED | SUPPORT AREA(S) INVOLVED | TIME PERIOD PROPOSED
VALUE-ADDING ACTIONS
Climate resilience | To contribute, with other partipants, to the contrustion of skills for the community resilience to climate change. | Alliance for resilience to climate change | To establish a participation and alliance encouragement strategy for climate resilience in order to contribute to the strengthening of local comunity and institutional skils directed to the mitigation of the impacts on human rights derived from climate change. | - Sustainable Development Management | - Office of the Assistant Director of Social Management - Sustainable Development Management | Second semester 2021
Alignment with the Sustainable Development Strategy | To align the sustainable development strategy with human rights | Inclusion of the rights approach in the actions to contribute in the framework of the Transformation of Territories | To establish criteria for the contribution to human rights in the constructio of Sustainable Development Agendas with stakeholders in each territory, and to define specificcontribution indicators for overcoming problems, as well as for local skill-building regarding human rights. To establish an prioritized work approach or "flagship" regarding human rights, which positions TGI in this field, and helps to concentrate efforts in order to generate and show actual impacts to the contribution for the enforcement of human rights. | - Sustainable Development Management | - Sustainable Development Management | First semester 2021
Environment | To coordinate actions in favor of the environment with other participants in the territory | Prevention campaign regarding sound emissions | To encourage, along with institutional allies (National Police Force, Healthcare and Environment Secretariats, Schools, Academia) an awareness and prevention campaign for sound contamination in the most critical towns. | - Sustainable Development Management | - Office of the Assistant Director of Social Management - Sustainable Development Management | Second semester 2021

## Risks
RISKS
R3 | Impact to enthnic communities' rights
R9 | Impact to the right to work in safe and dignified conditions.
R10 | Impact to the populations rights due to abuse of authority and excess in the use of force by private security.
R2 | Impact to the right to a dignified home.
R1 | Impact to the right to a clean environment.
R6 | Impact to the right of equality due to gender-based reasons.
R8 | Impact to the right of special protection to children and adolescents.
R7 | Impact to the freedom of information right
R5 | Impact to victims requesting restitution and/or already restituted
R4 | Impact to economic rights